## Categorias (hidden)
Aquisição de patentes e direitos de propriedade
Matérias-primas e materiais consumíveis
Aquisição de componentes
Consultoria
Estudos/Relatórios DNSH
Assistência técnica
Aquisição de serviços
Equipamento informático
Software e licenças
Máquinas e equipamentos
Aquisição de instrumentos e equipamento científico e técnico
Registo de patentes (Taxas Oficiais)
Registo de modelo de utilidade e de desenho ou modelo (Taxas Oficiais)
Promoção e divulgação
Seminários e Conferências
Feiras e exposições
Deslocações
Estadias
Processos de certificação
Auditorias
CC/ROC

## Tecnicos
ID | Beneficiário | Nova | NIF | Nome/Perfil (colocar perfis) | Nível | Vínculo | Vencimento mês (Consultar SAAF para Valores) | Seguro Social Voluntário | Seguro Acidentes Pessoais | Taxa Segurança Social | Critico | Custo ETI
|  | Não |  | D1 - Operations Management Specialist | Nível 8 - Doutorado | Quadro de Cedência Ocasional [Docentes] | 5227.28 | 0 | 0 | 22.3% |  | 8136.4989
|  | Não |  | C1 - Digital Architecture Specialist | Nível 6 - Licenciado | Contrato de Trablho a Termo Incerto | 4593.99 | 0 | 0 | 22.3% | Sim | 7150.7543
|  | Não |  | C2 - Simulation and Digital Twin Specialist | Nível 7 - Mestre | Contrato de Trablho a Termo Incerto | 2902.17 | 0 | 0 | 22.3% |  | 4517.3595
|  | Não |  | C3 - Digital Architeture and Data Infrastructure Specialist | Nível 7 - Mestre | Contrato de Trablho a Termo Incerto | 1896.07 | 0 | 0 | 22.3% |  | 2951.3191
|  | Não |  | C4 - Digital Architeture and Data Infrastructure Specialist | Nível 7 - Mestre | Contrato de Trablho a Termo Incerto | 4029.99 | 0 | 0 | 22.3% |  | 6272.8626
|  | Não |  | D2 - Technology Adoption Specialist | Nível 8 - Doutorado | Quadro de Cedência Ocasional [Docentes] | 3393.14 | 0 | 0 | 22.3% |  | 5281.5766
|  | Não |  | D3 - Data Management Specialist | Nível 8 - Doutorado | Quadro de Cedência Ocasional [Docentes] | 4035.1 | 0 | 0 | 22.3% | Sim | 6280.8166
|  | Não |  | D4 - Data Analytics Specialist | Nível 8 - Doutorado | Quadro de Cedência Ocasional [Docentes] | 4218.5 | 0 | 0 | 22.3% |  | 6566.287
|  | Não |  | C5 - Software Development Specialist | Nível 7 - Mestre | Contrato de Trablho a Termo Incerto | 2229.65 | 0 | 0 | 22.3% |  | 3470.5516
|  | Não |  | C6 - Simulation and Digital Twin Specialist | Nível 7 - Mestre | Contrato de Trablho a Termo Incerto | 1812.2 | 0 | 0 | 22.3% |  | 2820.7717
|  | Não |  | D5 - Operations Management and Data Analytics Specialist | Nível 8 - Doutorado | Quadro de Cedência Ocasional [Docentes] | 3851.67 | 0 | 0 | 22.3% |  | 5995.2994
[8 empty] | 0 | 0 | 22.3% |  | 0
[8 empty] | 0 | 0 | 22.3% |  | 0
[8 empty] | 0 | 0 | 22.3% |  | 0
[8 empty] | 0 | 0 | 22.3% |  | 0
[8 empty] | 0 | 0 | 22.3% |  | 0
[8 empty] | 0 | 0 | 22.3% |  | 0
[8 empty] | 0 | 0 | 22.3% |  | 0
[8 empty] | 0 | 0 | 22.3% |  | 0

## Folha1
Rótulos de Linha | Soma de ETI 0 (Ano 2027) | Soma de ETI 1 (Ano 2028) | Soma de ET2 (Ano 2029)
C1 - Digital Architecture Specialist | 5 | 5 | 5
C2 - Simulation and Digital Twin Specialist | 5 | 5 | 5
C3 - Digital Architeture and Data Infrastructure Specialist | 5 | 5 | 5
C4 - Digital Architeture and Data Infrastructure Specialist | 5 | 5 | 5
C5 - Software Development Specialist | 8 | 8 | 8.0833
C6 - Simulation and Digital Twin Specialist | 8 | 8 | 8.0833
D1 - Operations Management Specialist | 3 | 3 | 3
D2 - Technology Adoption Specialist | 3 | 3 | 3
D3 - Data Management Specialist | 3 | 3 | 3
D4 - Data Analytics Specialist | 4 | 4 | 4
D5 - Operations Management and Data Analytics Specialist | 2.5 | 2.5 | 2.4857
(em branco)
Total Geral | 51.5 | 51.5 | 51.6524

## Pessoal
N.º | Técnico | Conteúdo Funcional | Estab. | Atividade | ETI 0 (Ano 2027) | ETI 1 (Ano 2028) | ET2 (Ano 2029) | ET3 (Ano 2030) | Valor (Custo Total Pessoal) | Custo ETI (Ano 2027) | Custo ETI (Ano 2028) | Custo ETI (Ano 2029) | Custo ETI (Ano 2030)
| D1 - Operations Management Specialist | [7 empty] | 0 | 0 | 0 | 0 | 0
| C1 - Digital Architecture Specialist | [7 empty] | 0 | 0 | 0 | 0 | 0
| C2 - Simulation and Digital Twin Specialist | [7 empty] | 0 | 0 | 0 | 0 | 0
| C3 - Digital Architeture and Data Infrastructure Specialist | [7 empty] | 0 | 0 | 0 | 0 | 0
| C4 - Digital Architeture and Data Infrastructure Specialist | [7 empty] | 0 | 0 | 0 | 0 | 0
| D2 - Technology Adoption Specialist | [7 empty] | 0 | 0 | 0 | 0 | 0
| D3 - Data Management Specialist | [7 empty] | 0 | 0 | 0 | 0 | 0
| D4 - Data Analytics Specialist | [7 empty] | 0 | 0 | 0 | 0 | 0
| C5 - Software Development Specialist | [7 empty] | 0 | 0 | 0 | 0 | 0
| C6 - Simulation and Digital Twin Specialist | [7 empty] | 0 | 0 | 0 | 0 | 0
| D5 - Operations Management and Data Analytics Specialist | [7 empty] | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0
| D1 - Operations Management Specialist |  |  | A1 State of the art and technological surveillance | 3 |  |  |  | 73228.4903 | 24409.4968 | 0 | 0 | 0
| C1 - Digital Architecture Specialist |  |  | A1 State of the art and technological surveillance | 1 |  |  |  | 7150.7543 | 7150.7543 | 0 | 0 | 0
| C2 - Simulation and Digital Twin Specialist |  |  | A1 State of the art and technological surveillance | 1 |  |  |  | 4517.3595 | 4517.3595 | 0 | 0 | 0
| C3 - Digital Architeture and Data Infrastructure Specialist |  |  | A1 State of the art and technological surveillance | 1 |  |  |  | 2951.3191 | 2951.3191 | 0 | 0 | 0
| C4 - Digital Architeture and Data Infrastructure Specialist |  |  | A1 State of the art and technological surveillance | 1 |  |  |  | 6272.8626 | 6272.8626 | 0 | 0 | 0
| D2 - Technology Adoption Specialist |  |  | A1 State of the art and technological surveillance | 3 |  |  |  | 47534.1898 | 15844.7299 | 0 | 0 | 0
| D3 - Data Management Specialist |  |  | A1 State of the art and technological surveillance | 3 |  |  |  | 56527.3491 | 18842.4497 | 0 | 0 | 0
| D4 - Data Analytics Specialist |  |  | A1 State of the art and technological surveillance | 1 |  |  |  | 6566.287 | 6566.287 | 0 | 0 | 0
| C5 - Software Development Specialist |  |  | A1 State of the art and technological surveillance | 1 |  |  |  | 3470.5516 | 3470.5516 | 0 | 0 | 0
| C6 - Simulation and Digital Twin Specialist |  |  | A1 State of the art and technological surveillance | 1 |  |  |  | 2820.7717 | 2820.7717 | 0 | 0 | 0
| D5 - Operations Management and Data Analytics Specialist |  |  | A1 State of the art and technological surveillance | 1 |  |  |  | 5995.2994 | 5995.2994 | 0 | 0 | 0 | 11%
[9 empty] | 0 | 0 | 0 | 0 | 0
| D1 - Operations Management Specialist |  |  | A4 Digital twin development | 0 | 1 | 0.4 |  | 0 | 0 | 8136.4989 | 3254.5996 | 0
| C1 - Digital Architecture Specialist |  |  | A4 Digital twin development | 3 | 2 | 0.8 |  | 124423.124 | 21452.2628 | 14301.5085 | 5720.6034 | 0
| C2 - Simulation and Digital Twin Specialist |  |  | A4 Digital twin development | 4 | 3 | 1.2 |  | 148169.3923 | 18069.4381 | 13552.0786 | 5420.8314 | 0
| C3 - Digital Architeture and Data Infrastructure Specialist |  |  | A4 Digital twin development | 4 | 3 | 1.2 |  | 96803.2678 | 11805.2766 | 8853.9574 | 3541.583 | 0
| C4 - Digital Architeture and Data Infrastructure Specialist |  |  | A4 Digital twin development | 4 | 3 | 1.2 |  | 205749.8938 | 25091.4505 | 18818.5878 | 7527.4351 | 0
| D2 - Technology Adoption Specialist |  |  | A4 Digital twin development | 0 | 1 | 0.4 |  | 0 | 0 | 5281.5766 | 2112.6307 | 0
| D3 - Data Management Specialist |  |  | A4 Digital twin development | 0 | 1 | 0.4 |  | 0 | 0 | 6280.8166 | 2512.3266 | 0
| D4 - Data Analytics Specialist |  |  | A4 Digital twin development | 3 | 2 | 0.8 |  | 114253.3938 | 19698.861 | 13132.574 | 5253.0296 | 0
| C5 - Software Development Specialist |  |  | A4 Digital twin development | 7 | 7 | 2.4 |  | 398419.3205 | 24293.861 | 24293.861 | 8329.3238 | 0
| C6 - Simulation and Digital Twin Specialist |  |  | A4 Digital twin development | 7 | 7 | 2.4 |  | 323824.588 | 19745.4017 | 19745.4017 | 6769.852 | 0
| D5 - Operations Management and Data Analytics Specialist |  |  | A4 Digital twin development | 1.5 | 1.5 | 0.4 |  | 30576.0271 | 8992.9491 | 8992.9491 | 2398.1198 | 0 | 49.58%
[9 empty] | 0 | 0 | 0 | 0 | 0
| D1 - Operations Management Specialist |  |  | A5 Integration and validation in industrial environment |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| C1 - Digital Architecture Specialist |  |  | A5 Integration and validation in industrial environment |  | 1 | 1.4 |  | 0 | 0 | 7150.7543 | 10011.056 | 0
| C2 - Simulation and Digital Twin Specialist |  |  | A5 Integration and validation in industrial environment |  | 1 | 3.2 |  | 0 | 0 | 4517.3595 | 14455.5505 | 0
| C3 - Digital Architeture and Data Infrastructure Specialist |  |  | A5 Integration and validation in industrial environment |  | 1 | 2 |  | 0 | 0 | 2951.3191 | 5902.6383 | 0
| C4 - Digital Architeture and Data Infrastructure Specialist |  |  | A5 Integration and validation in industrial environment |  | 1 | 3.2 |  | 0 | 0 | 6272.8626 | 20073.1604 | 0
| D2 - Technology Adoption Specialist |  |  | A5 Integration and validation in industrial environment |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| D3 - Data Management Specialist |  |  | A5 Integration and validation in industrial environment |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| D4 - Data Analytics Specialist |  |  | A5 Integration and validation in industrial environment |  | 1 | 0 |  | 0 | 0 | 6566.287 | 0 | 0
| C5 - Software Development Specialist |  |  | A5 Integration and validation in industrial environment |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| C6 - Simulation and Digital Twin Specialist |  |  | A5 Integration and validation in industrial environment |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| D5 - Operations Management and Data Analytics Specialist |  |  | A5 Integration and validation in industrial environment |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 9.579%
[9 empty] | 0 | 0 | 0 | 0 | 0
| D1 - Operations Management Specialist |  |  | A6 Digital twin industrial integration |  | 0.5 | 0.6 |  | 0 | 0 | 4068.2495 | 4881.8994 | 0
| C1 - Digital Architecture Specialist |  |  | A6 Digital twin industrial integration |  | 0.5 | 0.6 |  | 0 | 0 | 3575.3771 | 4290.4526 | 0
| C2 - Simulation and Digital Twin Specialist |  |  | A6 Digital twin industrial integration |  | 0.5 | 0.6 |  | 0 | 0 | 2258.6798 | 2710.4157 | 0
| C3 - Digital Architeture and Data Infrastructure Specialist |  |  | A6 Digital twin industrial integration |  | 0.5 | 0.6 |  | 0 | 0 | 1475.6596 | 1770.7915 | 0
| C4 - Digital Architeture and Data Infrastructure Specialist |  |  | A6 Digital twin industrial integration |  | 0.5 | 0.6 |  | 0 | 0 | 3136.4313 | 3763.7176 | 0
| D2 - Technology Adoption Specialist |  |  | A6 Digital twin industrial integration |  | 0.5 | 0.4 |  | 0 | 0 | 2640.7883 | 2112.6307 | 0
| D3 - Data Management Specialist |  |  | A6 Digital twin industrial integration |  | 0.5 | 0.4 |  | 0 | 0 | 3140.4083 | 2512.3266 | 0
| D4 - Data Analytics Specialist |  |  | A6 Digital twin industrial integration |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| C5 - Software Development Specialist |  |  | A6 Digital twin industrial integration |  | 0.5 | 4.4833 |  | 0 | 0 | 1735.2758 | 15559.6396 | 0
| C6 - Simulation and Digital Twin Specialist |  |  | A6 Digital twin industrial integration |  | 0.5 | 4.4833 |  | 0 | 0 | 1410.3858 | 12646.4597 | 0
| D5 - Operations Management and Data Analytics Specialist |  |  | A6 Digital twin industrial integration |  | 0 | 1.0857 |  | 0 | 0 | 0 | 6509.1822 | 0 | 11.88%
[9 empty] | 0 | 0 | 0 | 0 | 0
| D1 - Operations Management Specialist |  |  | A7 Industrial implementation of solutions |  | 0.5 | 1 |  | 0 | 0 | 4068.2495 | 8136.4989 | 0
| C1 - Digital Architecture Specialist |  |  | A7 Industrial implementation of solutions |  | 0.5 | 1.2 |  | 0 | 0 | 3575.3771 | 8580.9051 | 0
| C2 - Simulation and Digital Twin Specialist |  |  | A7 Industrial implementation of solutions |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| C3 - Digital Architeture and Data Infrastructure Specialist |  |  | A7 Industrial implementation of solutions |  | 0.5 | 1.2 |  | 0 | 0 | 1475.6596 | 3541.583 | 0
| C4 - Digital Architeture and Data Infrastructure Specialist |  |  | A7 Industrial implementation of solutions |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| D2 - Technology Adoption Specialist |  |  | A7 Industrial implementation of solutions |  | 0.5 | 1.2 |  | 0 | 0 | 2640.7883 | 6337.892 | 0
| D3 - Data Management Specialist |  |  | A7 Industrial implementation of solutions |  | 0.5 | 1.2 |  | 0 | 0 | 3140.4083 | 7536.9799 | 0
| D4 - Data Analytics Specialist |  |  | A7 Industrial implementation of solutions |  | 0 | 2.2 |  | 0 | 0 | 0 | 14445.8314 | 0
| C5 - Software Development Specialist |  |  | A7 Industrial implementation of solutions |  | 0.5 | 1.2 |  | 0 | 0 | 1735.2758 | 4164.6619 | 0
| C6 - Simulation and Digital Twin Specialist |  |  | A7 Industrial implementation of solutions |  | 0.5 | 1.2 |  | 0 | 0 | 1410.3858 | 3384.926 | 0
| D5 - Operations Management and Data Analytics Specialist |  |  | A7 Industrial implementation of solutions |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 8.997%
[9 empty] | 0 | 0 | 0 | 0 | 0
| D1 - Operations Management Specialist |  |  | A8 Promotion and dissemination of the results |  | 1 | 1 |  | 0 | 0 | 8136.4989 | 8136.4989 | 0
| C1 - Digital Architecture Specialist |  |  | A8 Promotion and dissemination of the results |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| C2 - Simulation and Digital Twin Specialist |  |  | A8 Promotion and dissemination of the results |  | 0.5 | 0 |  | 0 | 0 | 2258.6798 | 0 | 0
| C3 - Digital Architeture and Data Infrastructure Specialist |  |  | A8 Promotion and dissemination of the results |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| C4 - Digital Architeture and Data Infrastructure Specialist |  |  | A8 Promotion and dissemination of the results |  | 0.5 | 0 |  | 0 | 0 | 3136.4313 | 0 | 0
| D2 - Technology Adoption Specialist |  |  | A8 Promotion and dissemination of the results |  | 1 | 1 |  | 0 | 0 | 5281.5766 | 5281.5766 | 0
| D3 - Data Management Specialist |  |  | A8 Promotion and dissemination of the results |  | 1 | 1 |  | 0 | 0 | 6280.8166 | 6280.8166 | 0
| D4 - Data Analytics Specialist |  |  | A8 Promotion and dissemination of the results |  | 1 | 1 |  | 0 | 0 | 6566.287 | 6566.287 | 0
| C5 - Software Development Specialist |  |  | A8 Promotion and dissemination of the results |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| C6 - Simulation and Digital Twin Specialist |  |  | A8 Promotion and dissemination of the results |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| D5 - Operations Management and Data Analytics Specialist |  |  | A8 Promotion and dissemination of the results |  | 1 | 1 |  | 0 | 0 | 5995.2994 | 5995.2994 | 0 | 7.12%
| D1 - Operations Management Specialist |  |  | A9 Project management and implementation |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| C1 - Digital Architecture Specialist |  |  | A9 Project management and implementation | 1 | 1 | 1 |  | 21452.2628 | 7150.7543 | 7150.7543 | 7150.7543 | 0
| C2 - Simulation and Digital Twin Specialist |  |  | A9 Project management and implementation |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| C3 - Digital Architeture and Data Infrastructure Specialist |  |  | A9 Project management and implementation |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| C4 - Digital Architeture and Data Infrastructure Specialist |  |  | A9 Project management and implementation |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| D2 - Technology Adoption Specialist |  |  | A9 Project management and implementation |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| D3 - Data Management Specialist |  |  | A9 Project management and implementation |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| D4 - Data Analytics Specialist |  |  | A9 Project management and implementation |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| C5 - Software Development Specialist |  |  | A9 Project management and implementation |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| C6 - Simulation and Digital Twin Specialist |  |  | A9 Project management and implementation |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| D5 - Operations Management and Data Analytics Specialist |  |  | A9 Project management and implementation |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1.942%
[9 empty] | 0 | 0 | 0 | 0 | 0
[5 empty] | 51.5 | 51.5 | 51.6524 |  | C.Total/Ano | 255142.1366 | 255142.1366 | 255580.7664 | 0
| D1 - Operations Management Specialist |  |  |  | 3 | 3 | 3
| C1 - Digital Architecture Specialist |  |  |  | 5 | 5 | 5
| C2 - Simulation and Digital Twin Specialist |  |  |  | 5 | 5 | 5
| C3 - Digital Architeture and Data Infrastructure Specialist |  |  |  | 5 | 5 | 5
| C4 - Digital Architeture and Data Infrastructure Specialist |  |  |  | 5 | 5 | 5
| D2 - Technology Adoption Specialist |  |  |  | 3 | 3 | 3
| D3 - Data Management Specialist |  |  |  | 3 | 3 | 3
| D4 - Data Analytics Specialist |  |  |  | 4 | 4 | 4
| C5 - Software Development Specialist |  |  |  | 8 | 8 | 8.0833
| C6 - Simulation and Digital Twin Specialist |  |  |  | 8 | 8 | 8.0833
| D5 - Operations Management and Data Analytics Specialist |  |  |  | 2.5 | 2.5 | 2.4857
[5 empty] | 51.5 | 51.5 | 51.6524

## Custos
ID | Âmbito | N.º | Beneficiário | Estab. | Ativ. | Designação | Rubrica | Ano | Mês | Custo | EF
[7 empty] | Custos com Pessoal | 2027 |  | 255142.1366
[7 empty] | Custos com Pessoal | 2028 |  | 255142.1366
[7 empty] | Custos com Pessoal | 2029 |  | 255580.7664
[7 empty] | Custos com Pessoal | 2030 |  | 0
[5 empty] | Digital twin development | Hardware for data processing | Equipamento informático | 2027 | 4 | 20000
[5 empty] | Digital twin development | Digital Twin and Simulation Licenses | Software e licenças | 2027 | 4 | 15000
[5 empty] | Digital twin development | Digital Twin and Simulation Licenses | Software e licenças | 2028 | 1 | 15000
[5 empty] | Digital twin development | Digital Twin and Simulation Licenses | Software e licenças | 2029 | 1 | 15000
[5 empty] | Promotion and dissemination of the results | Registration of one person in two international conferences (e.g. FAIM2028 and IAMOT 2028) | Seminários e Conferências | 2028 | 1 | 1500
[5 empty] | Promotion and dissemination of the results | Registration of one person in two international conferences (e.g. FAIM2029 and IAMOT 2029) | Seminários e Conferências | 2029 | 1 | 1500
[5 empty] | Promotion and dissemination of the results | Trip of one person to two international conferences | Deslocações | 2028 | 1 | 2000
[5 empty] | Promotion and dissemination of the results | Trip of one person to two international conferences | Deslocações | 2029 | 1 | 2000
[5 empty] | Promotion and dissemination of the results | Hotel for one person, four nights, near of each international conference | Estadias | 2028 | 1 | 2000
[5 empty] | Promotion and dissemination of the results | Hotel for one person, four nights, near of each international conference | Estadias | 2029 | 1 | 2000
[5 empty] | Promotion and dissemination of the results | Open Access Journal | Promoção e divulgação | 2029 | 1 | 3000 |  | NOTA: Limite de 85,00€/noite por estadia em Hotel (DL 106/98) em território nacional; 148,91€/noite no estrangeiro
Orçamento Total
[12 empty] | 2027 | 310452.0861
[12 empty] | 2028 | 294937.0861
[12 empty] | 2029 | 298616.42
[12 empty] | 2030 | 0
[12 empty] | Total | 904005.5923
[7 empty] | Custos Indiretos | 2025 |  | 0
[7 empty] | Custos Indiretos | 2027 |  | 20309.9496
[7 empty] | Custos Indiretos | 2028 |  | 19294.9496
[7 empty] | Custos Indiretos | 2029 |  | 19535.6536

## Gantt
N. | Activity | Promoters | [6 empty] | 2027 | [11 empty] | 2028 | [11 empty] | 2029 | [11 empty] | 2030
[9 empty] | m1 | m2 | m3 | m4 | m5 | m6 | m7 | m8 | m9 | m10 | m11 | m12 | m13 | m14 | m15 | m16 | m17 | m18 | m19 | m20 | m21 | m22 | m23 | m24 | m25 | m26 | m27 | m28 | m29 | m30 | m31 | m32 | m33 | m34 | m35 | m36 | m37 | m38 | m39 | m40 | m41 | m42 | m43 | m44 | m45 | m46 | m47 | m48
|  | CARITÉ | RODIRO | DCSI PRO | OLIFEL | MIND | INESCTEC | CTCP | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | State of the art and technological surveillance | P | P | P | P | P | P | R | [48 empty] | 11% | Legend: | bar: 2027 m1 to 2027 m12
Transversal | bar: 2027 m1 to 2027 m12
1.1 | AI, computer vision and AR applied to footwear |  |  |  |  | x | x | x | [51 empty] | TRL 3→6 | bar: 2027 m1 to 2027 m10
TRL 6→8 | bar: 2027 m1 to 2027 m10
1.2 | Adaptive robotics and laser for flexible materials | x | x | x |  |  | x | x | bar: 2027 m1 to 2027 m10
1.3 | Digital twins and intelligent factory orchestration | x | x |  | x |  | x | x | [50 empty] | R = Responsible (leader) ¦ P = Participant ¦ x = task contributor | bar: 2027 m1 to 2027 m10
1.4 | Technical requirements specification | x | x | x | x | x | x | x | bar: 2027 m3 to 2027 m12
1.5 | Technological surveillance of the target market |  |  | x | x | x | x | x | bar: 2027 m1 to 2027 m12
R02160-1 ¦ Américo Azevedo | D1 - Operations Management Specialist | [5 empty] | x |  | 2027 m1: 0.25; 2027 m2: 0.25; 2027 m3: 0.25; 2027 m4: 0.25; 2027 m5: 0.25; 2027 m6: 0.25; 2027 m7: 0.25; 2027 m8: 0.25; 2027 m9: 0.25; 2027 m10: 0.25; 2027 m11: 0.25; 2027 m12: 0.25
R03160 ¦ Rui Diogo Rebelo | C1 - Digital Architecture Specialist | [5 empty] | x |  | 2027 m1: 0.083333; 2027 m2: 0.083333; 2027 m3: 0.083333; 2027 m4: 0.083333; 2027 m5: 0.083333; 2027 m6: 0.083333; 2027 m7: 0.083333; 2027 m8: 0.083333; 2027 m9: 0.083333; 2027 m10: 0.083333; 2027 m11: 0.083333; 2027 m12: 0.083333
R07328 ¦ Romão Filipe Santos | C2 - Simulation and Digital Twin Specialist | [5 empty] | x |  | 2027 m1: 0.083333; 2027 m2: 0.083333; 2027 m3: 0.083333; 2027 m4: 0.083333; 2027 m5: 0.083333; 2027 m6: 0.083333; 2027 m7: 0.083333; 2027 m8: 0.083333; 2027 m9: 0.083333; 2027 m10: 0.083333; 2027 m11: 0.083333; 2027 m12: 0.083333
R07929 ¦ Ana Carolina Chaves | C3 - Digital Architeture and Data Infrastructure Specialist | [5 empty] | x |  | 2027 m1: 0.083333; 2027 m2: 0.083333; 2027 m3: 0.083333; 2027 m4: 0.083333; 2027 m5: 0.083333; 2027 m6: 0.083333; 2027 m7: 0.083333; 2027 m8: 0.083333; 2027 m9: 0.083333; 2027 m10: 0.083333; 2027 m11: 0.083333; 2027 m12: 0.083333
R00283 ¦ César Toscano | C4 - Digital Architeture and Data Infrastructure Specialist | [5 empty] | x |  | 2027 m1: 0.083333; 2027 m2: 0.083333; 2027 m3: 0.083333; 2027 m4: 0.083333; 2027 m5: 0.083333; 2027 m6: 0.083333; 2027 m7: 0.083333; 2027 m8: 0.083333; 2027 m9: 0.083333; 2027 m10: 0.083333; 2027 m11: 0.083333; 2027 m12: 0.083333
R08340 ¦ Hélio Cristiano Castro | D2 - Technology Adoption Specialist | [5 empty] | x |  | 2027 m1: 0.25; 2027 m2: 0.25; 2027 m3: 0.25; 2027 m4: 0.25; 2027 m5: 0.25; 2027 m6: 0.25; 2027 m7: 0.25; 2027 m8: 0.25; 2027 m9: 0.25; 2027 m10: 0.25; 2027 m11: 0.25; 2027 m12: 0.25
R04363 ¦ Cristovão Sousa | D3 - Data Management Specialist | [5 empty] | x |  | 2027 m1: 0.25; 2027 m2: 0.25; 2027 m3: 0.25; 2027 m4: 0.25; 2027 m5: 0.25; 2027 m6: 0.25; 2027 m7: 0.25; 2027 m8: 0.25; 2027 m9: 0.25; 2027 m10: 0.25; 2027 m11: 0.25; 2027 m12: 0.25
R05965 ¦ Luís Guimarães | D4 - Data Analytics Specialist | [5 empty] | x |  | 2027 m1: 0.083333; 2027 m2: 0.083333; 2027 m3: 0.083333; 2027 m4: 0.083333; 2027 m5: 0.083333; 2027 m6: 0.083333; 2027 m7: 0.083333; 2027 m8: 0.083333; 2027 m9: 0.083333; 2027 m10: 0.083333; 2027 m11: 0.083333; 2027 m12: 0.083333
R08941 ¦ Ricardo Ferreira | C5 - Software Development Specialist | [5 empty] | x |  | 2027 m1: 0.083333; 2027 m2: 0.083333; 2027 m3: 0.083333; 2027 m4: 0.083333; 2027 m5: 0.083333; 2027 m6: 0.083333; 2027 m7: 0.083333; 2027 m8: 0.083333; 2027 m9: 0.083333; 2027 m10: 0.083333; 2027 m11: 0.083333; 2027 m12: 0.083333
R08708 ¦ Henrique Piqueiro | C6 - Simulation and Digital Twin Specialist | [5 empty] | x |  | 2027 m1: 0.083333; 2027 m2: 0.083333; 2027 m3: 0.083333; 2027 m4: 0.083333; 2027 m5: 0.083333; 2027 m6: 0.083333; 2027 m7: 0.083333; 2027 m8: 0.083333; 2027 m9: 0.083333; 2027 m10: 0.083333; 2027 m11: 0.083333; 2027 m12: 0.083333
R06081 ¦ Gonçalo Reis Figueira | D5 - Operations Management and Data Analytics Specialist | [5 empty] | x |  | 2027 m1: 0.083333; 2027 m2: 0.083333; 2027 m3: 0.083333; 2027 m4: 0.083333; 2027 m5: 0.083333; 2027 m6: 0.083333; 2027 m7: 0.083333; 2027 m8: 0.083333; 2027 m9: 0.083333; 2027 m10: 0.083333; 2027 m11: 0.083333; 2027 m12: 0.083333
2 | AI, computer vision and AR solutions | P | P |  |  | R | P | P | bar: 2027 m4 to 2029 m28
2.1 | CV algorithms for colour-tone detection in leathers | x | x |  |  | x |  | x | bar: 2027 m4 to 2028 m16
2.2 | Generative AI for conceptual footwear design | x | x |  |  | x |  | x | bar: 2027 m4 to 2028 m20
2.3 | AI for digitisation and defect identification in leathers | x | x |  |  | x |  | x | bar: 2027 m6 to 2028 m22
2.4 | AR for interactive mould placement and piece collection | x | x |  |  | x |  | x | bar: 2027 m8 to 2028 m24
2.5 | AR for immersive 3D visualisation and design validation | x | x |  |  | x |  | x | bar: 2027 m8 to 2029 m26
2.6 | AI-optimised nesting engine (chromatic variations) | x | x |  |  | x |  | x | bar: 2027 m10 to 2029 m28
3 | Robotics, industrial vision and laser | P | P | R |  |  |  | P | bar: 2027 m4 to 2029 m28
3.1 | DCSI AI Vision Factory: vision systems and AI inspection software | x | x | x |  |  |  | x | bar: 2027 m4 to 2029 m28
3.2 | DCSI AI Robotic Factory: tooling, manipulation and assembly | x | x | x |  |  |  | x | bar: 2027 m4 to 2029 m28
3.3 | DCSI AI Laser Lab: 3D roughing, engraving and parameter validation | x | x | x |  |  |  | x | bar: 2027 m4 to 2029 m28
4 | Digital twin development |  |  |  | R |  | P | P | bar: 2027 m4 to 2029 m28
4.1 | Industrial mapping and priority use cases |  |  |  | x |  | x | x | bar: 2027 m4 to 2027 m10
4.2 | Functional architecture, data model and validation plan |  |  |  | x |  | x | x | bar: 2027 m6 to 2028 m14
4.3 | Digital model of upper-injection line (FOOTWEAR TWIN) |  |  |  | x |  | x | x | bar: 2027 m8 to 2028 m22
4.4 | Simulation, synchronisation and technical validation |  |  |  | x |  | x | x | bar: 2028 m14 to 2029 m26
4.5 | Planning, sequencing and re-planning algorithms (OPTIMIZE) |  |  |  | x |  | x | x | bar: 2027 m10 to 2028 m24
4.6 | Predictive models for quality, delay and maintenance |  |  |  | x |  | x | x | bar: 2027 m12 to 2029 m26
4.7 | Integration of FOOTWEAR TWIN + OPTIMIZE into ERP |  |  |  | x |  | x | x | bar: 2028 m20 to 2029 m28
R02160-1 ¦ Américo Azevedo | D1 - Operations Management Specialist | [5 empty] | x |  | 2028 m13: 0.083333; 2028 m14: 0.083333; 2028 m15: 0.083333; 2028 m16: 0.083333; 2028 m17: 0.083333; 2028 m18: 0.083333; 2028 m19: 0.083333; 2028 m20: 0.083333; 2028 m21: 0.083333; 2028 m22: 0.083333; 2028 m23: 0.083333; 2028 m24: 0.083333; 2029 m25: 0.1; 2029 m26: 0.1; 2029 m27: 0.1; 2029 m28: 0.1
R03160 ¦ Rui Diogo Rebelo | C1 - Digital Architecture Specialist | [5 empty] | x |  | 2027 m4: 0.33333; 2027 m5: 0.33333; 2027 m6: 0.33333; 2027 m7: 0.33333; 2027 m8: 0.33333; 2027 m9: 0.33333; 2027 m10: 0.33333; 2027 m11: 0.33333; 2027 m12: 0.33333; 2028 m13: 0.16667; 2028 m14: 0.16667; 2028 m15: 0.16667; 2028 m16: 0.16667; 2028 m17: 0.16667; 2028 m18: 0.16667; 2028 m19: 0.16667; 2028 m20: 0.16667; 2028 m21: 0.16667; 2028 m22: 0.16667; 2028 m23: 0.16667; 2028 m24: 0.16667; 2029 m25: 0.2; 2029 m26: 0.2; 2029 m27: 0.2; 2029 m28: 0.2
R07328 ¦ Romão Filipe Santos | C2 - Simulation and Digital Twin Specialist | [5 empty] | x |  | 2027 m4: 0.44444; 2027 m5: 0.44444; 2027 m6: 0.44444; 2027 m7: 0.44444; 2027 m8: 0.44444; 2027 m9: 0.44444; 2027 m10: 0.44444; 2027 m11: 0.44444; 2027 m12: 0.44444; 2028 m13: 0.25; 2028 m14: 0.25; 2028 m15: 0.25; 2028 m16: 0.25; 2028 m17: 0.25; 2028 m18: 0.25; 2028 m19: 0.25; 2028 m20: 0.25; 2028 m21: 0.25; 2028 m22: 0.25; 2028 m23: 0.25; 2028 m24: 0.25; 2029 m25: 0.3; 2029 m26: 0.3; 2029 m27: 0.3; 2029 m28: 0.3
R07929 ¦ Ana Carolina Chaves | C3 - Digital Architeture and Data Infrastructure Specialist | [5 empty] | x |  | 2027 m4: 0.44444; 2027 m5: 0.44444; 2027 m6: 0.44444; 2027 m7: 0.44444; 2027 m8: 0.44444; 2027 m9: 0.44444; 2027 m10: 0.44444; 2027 m11: 0.44444; 2027 m12: 0.44444; 2028 m13: 0.25; 2028 m14: 0.25; 2028 m15: 0.25; 2028 m16: 0.25; 2028 m17: 0.25; 2028 m18: 0.25; 2028 m19: 0.25; 2028 m20: 0.25; 2028 m21: 0.25; 2028 m22: 0.25; 2028 m23: 0.25; 2028 m24: 0.25; 2029 m25: 0.3; 2029 m26: 0.3; 2029 m27: 0.3; 2029 m28: 0.3
R00283 ¦ César Toscano | C4 - Digital Architeture and Data Infrastructure Specialist | [5 empty] | x |  | 2027 m4: 0.44444; 2027 m5: 0.44444; 2027 m6: 0.44444; 2027 m7: 0.44444; 2027 m8: 0.44444; 2027 m9: 0.44444; 2027 m10: 0.44444; 2027 m11: 0.44444; 2027 m12: 0.44444; 2028 m13: 0.25; 2028 m14: 0.25; 2028 m15: 0.25; 2028 m16: 0.25; 2028 m17: 0.25; 2028 m18: 0.25; 2028 m19: 0.25; 2028 m20: 0.25; 2028 m21: 0.25; 2028 m22: 0.25; 2028 m23: 0.25; 2028 m24: 0.25; 2029 m25: 0.3; 2029 m26: 0.3; 2029 m27: 0.3; 2029 m28: 0.3
R08340 ¦ Hélio Cristiano Castro | D2 - Technology Adoption Specialist | [5 empty] | x |  | 2028 m13: 0.083333; 2028 m14: 0.083333; 2028 m15: 0.083333; 2028 m16: 0.083333; 2028 m17: 0.083333; 2028 m18: 0.083333; 2028 m19: 0.083333; 2028 m20: 0.083333; 2028 m21: 0.083333; 2028 m22: 0.083333; 2028 m23: 0.083333; 2028 m24: 0.083333; 2029 m25: 0.1; 2029 m26: 0.1; 2029 m27: 0.1; 2029 m28: 0.1
R04363 ¦ Cristovão Sousa | D3 - Data Management Specialist | [5 empty] | x |  | 2028 m13: 0.083333; 2028 m14: 0.083333; 2028 m15: 0.083333; 2028 m16: 0.083333; 2028 m17: 0.083333; 2028 m18: 0.083333; 2028 m19: 0.083333; 2028 m20: 0.083333; 2028 m21: 0.083333; 2028 m22: 0.083333; 2028 m23: 0.083333; 2028 m24: 0.083333; 2029 m25: 0.1; 2029 m26: 0.1; 2029 m27: 0.1; 2029 m28: 0.1
R05965 ¦ Luís Guimarães | D4 - Data Analytics Specialist | [5 empty] | x |  | 2027 m4: 0.33333; 2027 m5: 0.33333; 2027 m6: 0.33333; 2027 m7: 0.33333; 2027 m8: 0.33333; 2027 m9: 0.33333; 2027 m10: 0.33333; 2027 m11: 0.33333; 2027 m12: 0.33333; 2028 m13: 0.16667; 2028 m14: 0.16667; 2028 m15: 0.16667; 2028 m16: 0.16667; 2028 m17: 0.16667; 2028 m18: 0.16667; 2028 m19: 0.16667; 2028 m20: 0.16667; 2028 m21: 0.16667; 2028 m22: 0.16667; 2028 m23: 0.16667; 2028 m24: 0.16667; 2029 m25: 0.2; 2029 m26: 0.2; 2029 m27: 0.2; 2029 m28: 0.2
R08941 ¦ Ricardo Ferreira | C5 - Software Development Specialist | [5 empty] | x |  | 2027 m4: 0.77778; 2027 m5: 0.77778; 2027 m6: 0.77778; 2027 m7: 0.77778; 2027 m8: 0.77778; 2027 m9: 0.77778; 2027 m10: 0.77778; 2027 m11: 0.77778; 2027 m12: 0.77778; 2028 m13: 0.58333; 2028 m14: 0.58333; 2028 m15: 0.58333; 2028 m16: 0.58333; 2028 m17: 0.58333; 2028 m18: 0.58333; 2028 m19: 0.58333; 2028 m20: 0.58333; 2028 m21: 0.58333; 2028 m22: 0.58333; 2028 m23: 0.58333; 2028 m24: 0.58333; 2029 m25: 0.6; 2029 m26: 0.6; 2029 m27: 0.6; 2029 m28: 0.6
R08708 ¦ Henrique Piqueiro | C6 - Simulation and Digital Twin Specialist | [5 empty] | x |  | 2027 m4: 0.77778; 2027 m5: 0.77778; 2027 m6: 0.77778; 2027 m7: 0.77778; 2027 m8: 0.77778; 2027 m9: 0.77778; 2027 m10: 0.77778; 2027 m11: 0.77778; 2027 m12: 0.77778; 2028 m13: 0.58333; 2028 m14: 0.58333; 2028 m15: 0.58333; 2028 m16: 0.58333; 2028 m17: 0.58333; 2028 m18: 0.58333; 2028 m19: 0.58333; 2028 m20: 0.58333; 2028 m21: 0.58333; 2028 m22: 0.58333; 2028 m23: 0.58333; 2028 m24: 0.58333; 2029 m25: 0.6; 2029 m26: 0.6; 2029 m27: 0.6; 2029 m28: 0.6
R06081 ¦ Gonçalo Reis Figueira | D5 - Operations Management and Data Analytics Specialist | [5 empty] | x |  | 2027 m4: 0.16667; 2027 m5: 0.16667; 2027 m6: 0.16667; 2027 m7: 0.16667; 2027 m8: 0.16667; 2027 m9: 0.16667; 2027 m10: 0.16667; 2027 m11: 0.16667; 2027 m12: 0.16667; 2028 m13: 0.125; 2028 m14: 0.125; 2028 m15: 0.125; 2028 m16: 0.125; 2028 m17: 0.125; 2028 m18: 0.125; 2028 m19: 0.125; 2028 m20: 0.125; 2028 m21: 0.125; 2028 m22: 0.125; 2028 m23: 0.125; 2028 m24: 0.125; 2029 m25: 0.1; 2029 m26: 0.1; 2029 m27: 0.1; 2029 m28: 0.1
5 | Integration and validation in industrial environment | P | P | R | P | P | P | P | bar: 2028 m16 to 2029 m34
5.1 | Vision HW and AI algorithms in Quality Gates (QG) |  |  | x |  | x |  | x | bar: 2028 m16 to 2029 m26
5.2 | Adaptive robotic cell for uppers: assembly and calibration |  |  | x |  |  |  | x | bar: 2028 m16 to 2029 m28
5.3 | AI/CV/AR integration into CAD systems and cutting machines |  |  | x |  | x |  | x | bar: 2028 m18 to 2029 m28
5.4 | Closed-loop quality control implementation |  |  | x | x | x | x | x | bar: 2028 m20 to 2029 m30
5.5 | Full validation at CARITÉ (scan > laser > injection > QG) | x |  | x | x |  |  | x | bar: 2028 m24 to 2029 m34
5.6 | Modular validation at RODIRO (QG on existing lines) |  | x | x | x |  |  | x | bar: 2028 m24 to 2029 m32
x | bar: 2028 m24 to 2029 m32
5.7 | Environmental impact and sustainability assessment |  |  | x |  |  |  | x | bar: 2029 m28 to 2029 m34
R02160-1 ¦ Américo Azevedo | D1 - Operations Management Specialist | [5 empty] | x
R03160 ¦ Rui Diogo Rebelo | C1 - Digital Architecture Specialist | [5 empty] | x |  | 2028 m16: 0.11111; 2028 m17: 0.11111; 2028 m18: 0.11111; 2028 m19: 0.11111; 2028 m20: 0.11111; 2028 m21: 0.11111; 2028 m22: 0.11111; 2028 m23: 0.11111; 2028 m24: 0.11111; 2029 m25: 0.2; 2029 m26: 0.2; 2029 m27: 0.2; 2029 m28: 0.2; 2029 m29: 0.2; 2029 m30: 0.2; 2029 m31: 0.2
R07328 ¦ Romão Filipe Santos | C2 - Simulation and Digital Twin Specialist | [5 empty] | x |  | 2028 m16: 0.11111; 2028 m17: 0.11111; 2028 m18: 0.11111; 2028 m19: 0.11111; 2028 m20: 0.11111; 2028 m21: 0.11111; 2028 m22: 0.11111; 2028 m23: 0.11111; 2028 m24: 0.11111; 2029 m25: 0.32; 2029 m26: 0.32; 2029 m27: 0.32; 2029 m28: 0.32; 2029 m29: 0.32; 2029 m30: 0.32; 2029 m31: 0.32; 2029 m32: 0.32; 2029 m33: 0.32; 2029 m34: 0.32
R07929 ¦ Ana Carolina Chaves | C3 - Digital Architeture and Data Infrastructure Specialist | [5 empty] | x |  | 2028 m16: 0.11111; 2028 m17: 0.11111; 2028 m18: 0.11111; 2028 m19: 0.11111; 2028 m20: 0.11111; 2028 m21: 0.11111; 2028 m22: 0.11111; 2028 m23: 0.11111; 2028 m24: 0.11111; 2029 m25: 0.2; 2029 m26: 0.2; 2029 m27: 0.2; 2029 m28: 0.2; 2029 m29: 0.2; 2029 m30: 0.2; 2029 m31: 0.2; 2029 m32: 0.2; 2029 m33: 0.2; 2029 m34: 0.2
R00283 ¦ César Toscano | C4 - Digital Architeture and Data Infrastructure Specialist | [5 empty] | x |  | 2028 m16: 0.11111; 2028 m17: 0.11111; 2028 m18: 0.11111; 2028 m19: 0.11111; 2028 m20: 0.11111; 2028 m21: 0.11111; 2028 m22: 0.11111; 2028 m23: 0.11111; 2028 m24: 0.11111; 2029 m25: 0.32; 2029 m26: 0.32; 2029 m27: 0.32; 2029 m28: 0.32; 2029 m29: 0.32; 2029 m30: 0.32; 2029 m31: 0.32; 2029 m32: 0.32; 2029 m33: 0.32; 2029 m34: 0.32
R08340 ¦ Hélio Cristiano Castro | D2 - Technology Adoption Specialist | [5 empty] | x
R04363 ¦ Cristovão Sousa | D3 - Data Management Specialist | [5 empty] | x
R05965 ¦ Luís Guimarães | D4 - Data Analytics Specialist | [5 empty] | x |  | 2028 m16: 0.11111; 2028 m17: 0.11111; 2028 m18: 0.11111; 2028 m19: 0.11111; 2028 m20: 0.11111; 2028 m21: 0.11111; 2028 m22: 0.11111; 2028 m23: 0.11111; 2028 m24: 0.11111
R08941 ¦ Ricardo Ferreira | C5 - Software Development Specialist | [5 empty] | x
R08708 ¦ Henrique Piqueiro | C6 - Simulation and Digital Twin Specialist | [5 empty] | x
R06081 ¦ Gonçalo Reis Figueira | D5 - Operations Management and Data Analytics Specialist | [5 empty] | x
6 | Digital twin industrial integration | P |  |  | R |  | P | P | bar: 2028 m16 to 2029 m30
6.1 | Pilot implementation at CARITÉ and user adaptation | x |  |  | x |  | x | x | bar: 2028 m16 to 2028 m24
6.2 | Industrial validation of FOOTWEAR TWIN and OPTIMIZE | x |  |  | x |  | x | x | bar: 2028 m20 to 2029 m28
6.3 | Operational, economic and strategic impact measurement |  |  |  | x |  | x | x | bar: 2028 m24 to 2029 m30
R02160-1 ¦ Américo Azevedo | D1 - Operations Management Specialist | [5 empty] | x |  | 2028 m16: 0.055556; 2028 m17: 0.055556; 2028 m18: 0.055556; 2028 m19: 0.055556; 2028 m20: 0.055556; 2028 m21: 0.055556; 2028 m22: 0.055556; 2028 m23: 0.055556; 2028 m24: 0.055556; 2029 m25: 0.1; 2029 m26: 0.1; 2029 m27: 0.1; 2029 m28: 0.1; 2029 m29: 0.1; 2029 m30: 0.1
R03160 ¦ Rui Diogo Rebelo | C1 - Digital Architecture Specialist | [5 empty] | x |  | 2028 m16: 0.055556; 2028 m17: 0.055556; 2028 m18: 0.055556; 2028 m19: 0.055556; 2028 m20: 0.055556; 2028 m21: 0.055556; 2028 m22: 0.055556; 2028 m23: 0.055556; 2028 m24: 0.055556; 2029 m25: 0.1; 2029 m26: 0.1; 2029 m27: 0.1; 2029 m28: 0.1; 2029 m29: 0.1; 2029 m30: 0.1
R07328 ¦ Romão Filipe Santos | C2 - Simulation and Digital Twin Specialist | [5 empty] | x |  | 2028 m16: 0.055556; 2028 m17: 0.055556; 2028 m18: 0.055556; 2028 m19: 0.055556; 2028 m20: 0.055556; 2028 m21: 0.055556; 2028 m22: 0.055556; 2028 m23: 0.055556; 2028 m24: 0.055556; 2029 m25: 0.1; 2029 m26: 0.1; 2029 m27: 0.1; 2029 m28: 0.1; 2029 m29: 0.1; 2029 m30: 0.1
R07929 ¦ Ana Carolina Chaves | C3 - Digital Architeture and Data Infrastructure Specialist | [5 empty] | x |  | 2028 m16: 0.055556; 2028 m17: 0.055556; 2028 m18: 0.055556; 2028 m19: 0.055556; 2028 m20: 0.055556; 2028 m21: 0.055556; 2028 m22: 0.055556; 2028 m23: 0.055556; 2028 m24: 0.055556; 2029 m25: 0.1; 2029 m26: 0.1; 2029 m27: 0.1; 2029 m28: 0.1; 2029 m29: 0.1; 2029 m30: 0.1
R00283 ¦ César Toscano | C4 - Digital Architeture and Data Infrastructure Specialist | [5 empty] | x |  | 2028 m16: 0.055556; 2028 m17: 0.055556; 2028 m18: 0.055556; 2028 m19: 0.055556; 2028 m20: 0.055556; 2028 m21: 0.055556; 2028 m22: 0.055556; 2028 m23: 0.055556; 2028 m24: 0.055556; 2029 m25: 0.1; 2029 m26: 0.1; 2029 m27: 0.1; 2029 m28: 0.1; 2029 m29: 0.1; 2029 m30: 0.1
R08340 ¦ Hélio Cristiano Castro | D2 - Technology Adoption Specialist | [5 empty] | x |  | 2028 m16: 0.055556; 2028 m17: 0.055556; 2028 m18: 0.055556; 2028 m19: 0.055556; 2028 m20: 0.055556; 2028 m21: 0.055556; 2028 m22: 0.055556; 2028 m23: 0.055556; 2028 m24: 0.055556; 2029 m25: 0.1; 2029 m26: 0.1; 2029 m27: 0.1; 2029 m28: 0.1
R04363 ¦ Cristovão Sousa | D3 - Data Management Specialist | [5 empty] | x |  | 2028 m16: 0.055556; 2028 m17: 0.055556; 2028 m18: 0.055556; 2028 m19: 0.055556; 2028 m20: 0.055556; 2028 m21: 0.055556; 2028 m22: 0.055556; 2028 m23: 0.055556; 2028 m24: 0.055556; 2029 m25: 0.1; 2029 m26: 0.1; 2029 m27: 0.1; 2029 m28: 0.1
R05965 ¦ Luís Guimarães | D4 - Data Analytics Specialist | [5 empty] | x
R08941 ¦ Ricardo Ferreira | C5 - Software Development Specialist | [5 empty] | x |  | 2028 m16: 0.055556; 2028 m17: 0.055556; 2028 m18: 0.055556; 2028 m19: 0.055556; 2028 m20: 0.055556; 2028 m21: 0.055556; 2028 m22: 0.055556; 2028 m23: 0.055556; 2028 m24: 0.055556; 2029 m25: 0.71667; 2029 m26: 0.71667; 2029 m27: 0.71667; 2029 m28: 0.71667; 2029 m29: 0.71667; 2029 m30: 0.9
R08708 ¦ Henrique Piqueiro | C6 - Simulation and Digital Twin Specialist | [5 empty] | x |  | 2028 m16: 0.055556; 2028 m17: 0.055556; 2028 m18: 0.055556; 2028 m19: 0.055556; 2028 m20: 0.055556; 2028 m21: 0.055556; 2028 m22: 0.055556; 2028 m23: 0.055556; 2028 m24: 0.055556; 2029 m25: 0.71667; 2029 m26: 0.71667; 2029 m27: 0.71667; 2029 m28: 0.71667; 2029 m29: 0.71667; 2029 m30: 0.9
R06081 ¦ Gonçalo Reis Figueira | D5 - Operations Management and Data Analytics Specialist | [5 empty] | x |  | 2029 m25: 0.15714; 2029 m26: 0.15714; 2029 m27: 0.15714; 2029 m28: 0.15714; 2029 m29: 0.15714; 2029 m30: 0.3
7 | Industrial implementation of solutions | R | P | P | P | P | P | P | bar: 2028 m18 to 2029 m36
7.1 | Industrialisation of AI technology products (MIND) |  |  |  |  | x |  | x | bar: 2028 m18 to 2029 m30
7.2 | Industrialisation of robotic cells and laser (DCSI PRO) |  |  | x |  |  |  | x | bar: 2028 m18 to 2029 m30
7.3 | ERP product and business model (OLIFEL) | x |  |  | x |  |  | x | bar: 2028 m18 to 2029 m30
7.4 | Definitive installation at CARITÉ (full demonstrator) | x |  | x | x | x | x | x | bar: 2028 m24 to 2029 m34
7.5 | Quality Gates installation at RODIRO (modular demonstrator) |  | x | x |  |  |  | x | bar: 2028 m24 to 2029 m36
7.6 | Acquisition of robotic lines, QC laboratory and software (RODIRO) |  |  | x |  |  |  | x | bar: 2028 m24 to 2029 m36
7.7 | Acquisition of laser robot, roughing line and injection machine (CARITÉ) | x | [5 empty] | x | bar: 2028 m24 to 2029 m36
R02160-1 ¦ Américo Azevedo | D1 - Operations Management Specialist | [5 empty] | x |  | 2028 m18: 0.071429; 2028 m19: 0.071429; 2028 m20: 0.071429; 2028 m21: 0.071429; 2028 m22: 0.071429; 2028 m23: 0.071429; 2028 m24: 0.071429; 2029 m25: 0.1; 2029 m26: 0.1; 2029 m27: 0.1; 2029 m28: 0.1; 2029 m29: 0.1; 2029 m30: 0.1; 2029 m31: 0.1; 2029 m32: 0.1; 2029 m33: 0.1; 2029 m34: 0.1
R03160 ¦ Rui Diogo Rebelo | C1 - Digital Architecture Specialist | [5 empty] | x |  | 2028 m18: 0.071429; 2028 m19: 0.071429; 2028 m20: 0.071429; 2028 m21: 0.071429; 2028 m22: 0.071429; 2028 m23: 0.071429; 2028 m24: 0.071429; 2029 m25: 0.1; 2029 m26: 0.1; 2029 m27: 0.1; 2029 m28: 0.1; 2029 m29: 0.1; 2029 m30: 0.1; 2029 m31: 0.1; 2029 m32: 0.1; 2029 m33: 0.1; 2029 m34: 0.1; 2029 m35: 0.1; 2029 m36: 0.1
R07328 ¦ Romão Filipe Santos | C2 - Simulation and Digital Twin Specialist | [5 empty] | x
R07929 ¦ Ana Carolina Chaves | C3 - Digital Architeture and Data Infrastructure Specialist | [5 empty] | x |  | 2028 m18: 0.071429; 2028 m19: 0.071429; 2028 m20: 0.071429; 2028 m21: 0.071429; 2028 m22: 0.071429; 2028 m23: 0.071429; 2028 m24: 0.071429; 2029 m25: 0.1; 2029 m26: 0.1; 2029 m27: 0.1; 2029 m28: 0.1; 2029 m29: 0.1; 2029 m30: 0.1; 2029 m31: 0.1; 2029 m32: 0.1; 2029 m33: 0.1; 2029 m34: 0.1; 2029 m35: 0.1; 2029 m36: 0.1
R00283 ¦ César Toscano | C4 - Digital Architeture and Data Infrastructure Specialist | [5 empty] | x
R08340 ¦ Hélio Cristiano Castro | D2 - Technology Adoption Specialist | [5 empty] | x |  | 2028 m18: 0.071429; 2028 m19: 0.071429; 2028 m20: 0.071429; 2028 m21: 0.071429; 2028 m22: 0.071429; 2028 m23: 0.071429; 2028 m24: 0.071429; 2029 m25: 0.1; 2029 m26: 0.1; 2029 m27: 0.1; 2029 m28: 0.1; 2029 m29: 0.1; 2029 m30: 0.1; 2029 m31: 0.1; 2029 m32: 0.1; 2029 m33: 0.1; 2029 m34: 0.1; 2029 m35: 0.1; 2029 m36: 0.1
R04363 ¦ Cristovão Sousa | D3 - Data Management Specialist | [5 empty] | x |  | 2028 m18: 0.071429; 2028 m19: 0.071429; 2028 m20: 0.071429; 2028 m21: 0.071429; 2028 m22: 0.071429; 2028 m23: 0.071429; 2028 m24: 0.071429; 2029 m25: 0.1; 2029 m26: 0.1; 2029 m27: 0.1; 2029 m28: 0.1; 2029 m29: 0.1; 2029 m30: 0.1; 2029 m31: 0.1; 2029 m32: 0.1; 2029 m33: 0.1; 2029 m34: 0.1; 2029 m35: 0.1; 2029 m36: 0.1
R05965 ¦ Luís Guimarães | D4 - Data Analytics Specialist | [5 empty] | x |  | 2029 m25: 0.18333; 2029 m26: 0.18333; 2029 m27: 0.18333; 2029 m28: 0.18333; 2029 m29: 0.18333; 2029 m30: 0.18333; 2029 m31: 0.18333; 2029 m32: 0.18333; 2029 m33: 0.18333; 2029 m34: 0.18333; 2029 m35: 0.18333; 2029 m36: 0.18333
R08941 ¦ Ricardo Ferreira | C5 - Software Development Specialist | [5 empty] | x |  | 2028 m18: 0.071429; 2028 m19: 0.071429; 2028 m20: 0.071429; 2028 m21: 0.071429; 2028 m22: 0.071429; 2028 m23: 0.071429; 2028 m24: 0.071429; 2029 m25: 0.1; 2029 m26: 0.1; 2029 m27: 0.1; 2029 m28: 0.1; 2029 m29: 0.1; 2029 m30: 0.1; 2029 m31: 0.1; 2029 m32: 0.1; 2029 m33: 0.1; 2029 m34: 0.1; 2029 m35: 0.1; 2029 m36: 0.1
R08708 ¦ Henrique Piqueiro | C6 - Simulation and Digital Twin Specialist | [5 empty] | x |  | 2028 m18: 0.071429; 2028 m19: 0.071429; 2028 m20: 0.071429; 2028 m21: 0.071429; 2028 m22: 0.071429; 2028 m23: 0.071429; 2028 m24: 0.071429; 2029 m25: 0.1; 2029 m26: 0.1; 2029 m27: 0.1; 2029 m28: 0.1; 2029 m29: 0.1; 2029 m30: 0.1; 2029 m31: 0.1; 2029 m32: 0.1; 2029 m33: 0.1; 2029 m34: 0.1; 2029 m35: 0.1; 2029 m36: 0.1
R06081 ¦ Gonçalo Reis Figueira | D5 - Operations Management and Data Analytics Specialist | [5 empty] | x
8 | Promotion and dissemination of the results | P | P | P | P | P | P | R | bar: 2027 m1 to 2029 m36
8.1 | Promotional material and project identity | x | x | x | x | x | x | x | bar: 2027 m1 to 2027 m12
8.2 | Technical-scientific publications |  |  | x | x | x | x | x | bar: 2027 m6 to 2029 m36
8.3 | Participation in scientific and specialist events |  |  | x | x | x | x | x | bar: 2027 m6 to 2029 m36
8.4 | Valorisation and commercial exploitation strategy | x | x | x | x | x | x | x | bar: 2028 m18 to 2029 m36
R02160-1 ¦ Américo Azevedo | D1 - Operations Management Specialist | [5 empty] | x |  | 2028 m13: 0.083333; 2028 m14: 0.083333; 2028 m15: 0.083333; 2028 m16: 0.083333; 2028 m17: 0.083333; 2028 m18: 0.083333; 2028 m19: 0.083333; 2028 m20: 0.083333; 2028 m21: 0.083333; 2028 m22: 0.083333; 2028 m23: 0.083333; 2028 m24: 0.083333; 2029 m25: 0.083333; 2029 m26: 0.083333; 2029 m27: 0.083333; 2029 m28: 0.083333; 2029 m29: 0.083333; 2029 m30: 0.083333; 2029 m31: 0.083333; 2029 m32: 0.083333; 2029 m33: 0.083333; 2029 m34: 0.083333; 2029 m35: 0.083333; 2029 m36: 0.083333
R03160 ¦ Rui Diogo Rebelo | C1 - Digital Architecture Specialist | [5 empty] | x
R07328 ¦ Romão Filipe Santos | C2 - Simulation and Digital Twin Specialist | [5 empty] | x |  | 2028 m13: 0.041667; 2028 m14: 0.041667; 2028 m15: 0.041667; 2028 m16: 0.041667; 2028 m17: 0.041667; 2028 m18: 0.041667; 2028 m19: 0.041667; 2028 m20: 0.041667; 2028 m21: 0.041667; 2028 m22: 0.041667; 2028 m23: 0.041667; 2028 m24: 0.041667
R07929 ¦ Ana Carolina Chaves | C3 - Digital Architeture and Data Infrastructure Specialist | [5 empty] | x
R00283 ¦ César Toscano | C4 - Digital Architeture and Data Infrastructure Specialist | [5 empty] | x |  | 2028 m13: 0.041667; 2028 m14: 0.041667; 2028 m15: 0.041667; 2028 m16: 0.041667; 2028 m17: 0.041667; 2028 m18: 0.041667; 2028 m19: 0.041667; 2028 m20: 0.041667; 2028 m21: 0.041667; 2028 m22: 0.041667; 2028 m23: 0.041667; 2028 m24: 0.041667
R08340 ¦ Hélio Cristiano Castro | D2 - Technology Adoption Specialist | [5 empty] | x |  | 2028 m13: 0.083333; 2028 m14: 0.083333; 2028 m15: 0.083333; 2028 m16: 0.083333; 2028 m17: 0.083333; 2028 m18: 0.083333; 2028 m19: 0.083333; 2028 m20: 0.083333; 2028 m21: 0.083333; 2028 m22: 0.083333; 2028 m23: 0.083333; 2028 m24: 0.083333; 2029 m25: 0.083333; 2029 m26: 0.083333; 2029 m27: 0.083333; 2029 m28: 0.083333; 2029 m29: 0.083333; 2029 m30: 0.083333; 2029 m31: 0.083333; 2029 m32: 0.083333; 2029 m33: 0.083333; 2029 m34: 0.083333; 2029 m35: 0.083333; 2029 m36: 0.083333
R04363 ¦ Cristovão Sousa | D3 - Data Management Specialist | [5 empty] | x |  | 2028 m13: 0.083333; 2028 m14: 0.083333; 2028 m15: 0.083333; 2028 m16: 0.083333; 2028 m17: 0.083333; 2028 m18: 0.083333; 2028 m19: 0.083333; 2028 m20: 0.083333; 2028 m21: 0.083333; 2028 m22: 0.083333; 2028 m23: 0.083333; 2028 m24: 0.083333; 2029 m25: 0.083333; 2029 m26: 0.083333; 2029 m27: 0.083333; 2029 m28: 0.083333; 2029 m29: 0.083333; 2029 m30: 0.083333; 2029 m31: 0.083333; 2029 m32: 0.083333; 2029 m33: 0.083333; 2029 m34: 0.083333; 2029 m35: 0.083333; 2029 m36: 0.083333
R05965 ¦ Luís Guimarães | D4 - Data Analytics Specialist | [5 empty] | x
R08941 ¦ Ricardo Ferreira | C5 - Software Development Specialist | [5 empty] | x
R08708 ¦ Henrique Piqueiro | C6 - Simulation and Digital Twin Specialist | [5 empty] | x
R06081 ¦ Gonçalo Reis Figueira | D5 - Operations Management and Data Analytics Specialist | [5 empty] | x |  | 2028 m13: 0.083333; 2028 m14: 0.083333; 2028 m15: 0.083333; 2028 m16: 0.083333; 2028 m17: 0.083333; 2028 m18: 0.083333; 2028 m19: 0.083333; 2028 m20: 0.083333; 2028 m21: 0.083333; 2028 m22: 0.083333; 2028 m23: 0.083333; 2028 m24: 0.083333; 2029 m25: 0.083333; 2029 m26: 0.083333; 2029 m27: 0.083333; 2029 m28: 0.083333; 2029 m29: 0.083333; 2029 m30: 0.083333; 2029 m31: 0.083333; 2029 m32: 0.083333; 2029 m33: 0.083333; 2029 m34: 0.083333; 2029 m35: 0.083333; 2029 m36: 0.083333
9 | Project management and implementation | P | P | P | P | P | P | R | bar: 2027 m1 to 2029 m36
9.1 | Technical, administrative and financial management | x | x | x | x | x | x | x | bar: 2027 m1 to 2029 m36
9.2 | Quality management and indicator monitoring | x | x | x | x | x | x | x | bar: 2027 m1 to 2029 m36
R02160-1 ¦ Américo Azevedo | D1 - Operations Management Specialist | [5 empty] | x
R03160 ¦ Rui Diogo Rebelo | C1 - Digital Architecture Specialist | [5 empty] | x
R07328 ¦ Romão Filipe Santos | C2 - Simulation and Digital Twin Specialist | [5 empty] | x |  | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333
R07929 ¦ Ana Carolina Chaves | C3 - Digital Architeture and Data Infrastructure Specialist | [5 empty] | x
R00283 ¦ César Toscano | C4 - Digital Architeture and Data Infrastructure Specialist | [5 empty] | x
R08340 ¦ Hélio Cristiano Castro | D2 - Technology Adoption Specialist | [5 empty] | x
R04363 ¦ Cristovão Sousa | D3 - Data Management Specialist | [5 empty] | x
R05965 ¦ Luís Guimarães | D4 - Data Analytics Specialist | [5 empty] | x
R08941 ¦ Ricardo Ferreira | C5 - Software Development Specialist | [5 empty] | x
R08708 ¦ Henrique Piqueiro | C6 - Simulation and Digital Twin Specialist | [5 empty] | x
R06081 ¦ Gonçalo Reis Figueira | D5 - Operations Management and Data Analytics Specialist | [5 empty] | x
A1 | State of the art and technological surveillance
R02160-1 ¦ Américo Azevedo | D1 - Operations Management Specialist | [7 empty] | 2027 m12: 3
R03160 ¦ Rui Diogo Rebelo | C1 - Digital Architecture Specialist | bar: 2027 m12
R07328 ¦ Romão Filipe Santos | C2 - Simulation and Digital Twin Specialist | bar: 2027 m12
R07929 ¦ Ana Carolina Chaves | C3 - Digital Architeture and Data Infrastructure Specialist | bar: 2027 m12
R00283 ¦ César Toscano | C4 - Digital Architeture and Data Infrastructure Specialist | bar: 2027 m12
R08340 ¦ Hélio Cristiano Castro | D2 - Technology Adoption Specialist | [7 empty] | 2027 m12: 3
R04363 ¦ Cristovão Sousa | D3 - Data Management Specialist | [7 empty] | 2027 m12: 3
R05965 ¦ Luís Guimarães | D4 - Data Analytics Specialist | bar: 2027 m12
R08941 ¦ Ricardo Ferreira | C5 - Software Development Specialist | bar: 2027 m12
R08708 ¦ Henrique Piqueiro | C6 - Simulation and Digital Twin Specialist | bar: 2027 m12
R06081 ¦ Gonçalo Reis Figueira | D5 - Operations Management and Data Analytics Specialist | bar: 2027 m12
A4 | Digital twin development | [7 empty] | 2027 m12: 17
R02160-1 ¦ Américo Azevedo | D1 - Operations Management Specialist | [7 empty] | 2027 m12: 0; 2028 m24: 1; 2029 m36: 0.4
R03160 ¦ Rui Diogo Rebelo | C1 - Digital Architecture Specialist | [7 empty] | 2027 m12: 3; 2028 m24: 2; 2029 m36: 0.8
R07328 ¦ Romão Filipe Santos | C2 - Simulation and Digital Twin Specialist | [7 empty] | 2027 m12: 4; 2028 m24: 3; 2029 m36: 1.2
R07929 ¦ Ana Carolina Chaves | C3 - Digital Architeture and Data Infrastructure Specialist | [7 empty] | 2027 m12: 4; 2028 m24: 3; 2029 m36: 1.2
R00283 ¦ César Toscano | C4 - Digital Architeture and Data Infrastructure Specialist | [7 empty] | 2027 m12: 4; 2028 m24: 3; 2029 m36: 1.2
R08340 ¦ Hélio Cristiano Castro | D2 - Technology Adoption Specialist | [7 empty] | 2027 m12: 0; 2028 m24: 1; 2029 m36: 0.4
R04363 ¦ Cristovão Sousa | D3 - Data Management Specialist | [7 empty] | 2027 m12: 0; 2028 m24: 1; 2029 m36: 0.4
R05965 ¦ Luís Guimarães | D4 - Data Analytics Specialist | [7 empty] | 2027 m12: 3; 2028 m24: 2; 2029 m36: 0.8
R08941 ¦ Ricardo Ferreira | C5 - Software Development Specialist | [7 empty] | 2027 m12: 7; 2028 m24: 7; 2029 m36: 2.4
R08708 ¦ Henrique Piqueiro | C6 - Simulation and Digital Twin Specialist | [7 empty] | 2027 m12: 7; 2028 m24: 7; 2029 m36: 2.4
R06081 ¦ Gonçalo Reis Figueira | D5 - Operations Management and Data Analytics Specialist | [7 empty] | 2027 m12: 1.5; 2028 m24: 1.5; 2029 m36: 0.4
33.5
50.5
A5 | Integration and validation in industrial environment
R02160-1 ¦ Américo Azevedo | D1 - Operations Management Specialist | [7 empty] | 2028 m24: 0; 2029 m36: 0
R03160 ¦ Rui Diogo Rebelo | C1 - Digital Architecture Specialist | [7 empty] | 2028 m24: 1; 2029 m36: 1.4
R07328 ¦ Romão Filipe Santos | C2 - Simulation and Digital Twin Specialist | [7 empty] | 2028 m24: 1; 2029 m36: 3.2
R07929 ¦ Ana Carolina Chaves | C3 - Digital Architeture and Data Infrastructure Specialist | [7 empty] | 2028 m24: 1; 2029 m36: 2
R00283 ¦ César Toscano | C4 - Digital Architeture and Data Infrastructure Specialist | [7 empty] | 2028 m24: 1; 2029 m36: 3.2
R08340 ¦ Hélio Cristiano Castro | D2 - Technology Adoption Specialist | [7 empty] | 2028 m24: 0; 2029 m36: 0
R04363 ¦ Cristovão Sousa | D3 - Data Management Specialist | [7 empty] | 2028 m24: 0; 2029 m36: 0
R05965 ¦ Luís Guimarães | D4 - Data Analytics Specialist | [7 empty] | 2028 m24: 1; 2029 m36: 0
R08941 ¦ Ricardo Ferreira | C5 - Software Development Specialist | [7 empty] | 2028 m24: 0; 2029 m36: 0
R08708 ¦ Henrique Piqueiro | C6 - Simulation and Digital Twin Specialist | [7 empty] | 2028 m24: 0; 2029 m36: 0
R06081 ¦ Gonçalo Reis Figueira | D5 - Operations Management and Data Analytics Specialist | [7 empty] | 2028 m24: 0; 2029 m36: 0
A6 | Digital twin industrial integration
R02160-1 ¦ Américo Azevedo | D1 - Operations Management Specialist | [7 empty] | 2028 m24: 0.5; 2029 m36: 0.6
R03160 ¦ Rui Diogo Rebelo | C1 - Digital Architecture Specialist | [7 empty] | 2028 m24: 0.5; 2029 m36: 0.6
R07328 ¦ Romão Filipe Santos | C2 - Simulation and Digital Twin Specialist | [7 empty] | 2028 m24: 0.5; 2029 m36: 0.6
R07929 ¦ Ana Carolina Chaves | C3 - Digital Architeture and Data Infrastructure Specialist | [7 empty] | 2028 m24: 0.5; 2029 m36: 0.6
R00283 ¦ César Toscano | C4 - Digital Architeture and Data Infrastructure Specialist | [7 empty] | 2028 m24: 0.5; 2029 m36: 0.6
R08340 ¦ Hélio Cristiano Castro | D2 - Technology Adoption Specialist | [7 empty] | 2028 m24: 0.5; 2029 m36: 0.4
R04363 ¦ Cristovão Sousa | D3 - Data Management Specialist | [7 empty] | 2028 m24: 0.5; 2029 m36: 0.4
R05965 ¦ Luís Guimarães | D4 - Data Analytics Specialist | [7 empty] | 2028 m24: 0; 2029 m36: 0
R08941 ¦ Ricardo Ferreira | C5 - Software Development Specialist | [7 empty] | 2028 m24: 0.5; 2029 m36: 4.4833
R08708 ¦ Henrique Piqueiro | C6 - Simulation and Digital Twin Specialist | [7 empty] | 2028 m24: 0.5; 2029 m36: 4.4833
R06081 ¦ Gonçalo Reis Figueira | D5 - Operations Management and Data Analytics Specialist | [7 empty] | 2028 m24: 0; 2029 m36: 1.0857
A7 | Industrial implementation of solutions
R02160-1 ¦ Américo Azevedo | D1 - Operations Management Specialist | [7 empty] | 2028 m24: 0.5; 2029 m36: 1
R03160 ¦ Rui Diogo Rebelo | C1 - Digital Architecture Specialist | [7 empty] | 2028 m24: 0.5; 2029 m36: 1.2
R07328 ¦ Romão Filipe Santos | C2 - Simulation and Digital Twin Specialist | [7 empty] | 2028 m24: 0; 2029 m36: 0
R07929 ¦ Ana Carolina Chaves | C3 - Digital Architeture and Data Infrastructure Specialist | [7 empty] | 2028 m24: 0.5; 2029 m36: 1.2
R00283 ¦ César Toscano | C4 - Digital Architeture and Data Infrastructure Specialist | [7 empty] | 2028 m24: 0; 2029 m36: 0
R08340 ¦ Hélio Cristiano Castro | D2 - Technology Adoption Specialist | [7 empty] | 2028 m24: 0.5; 2029 m36: 1.2
R04363 ¦ Cristovão Sousa | D3 - Data Management Specialist | [7 empty] | 2028 m24: 0.5; 2029 m36: 1.2
R05965 ¦ Luís Guimarães | D4 - Data Analytics Specialist | [7 empty] | 2028 m24: 0; 2029 m36: 2.2
R08941 ¦ Ricardo Ferreira | C5 - Software Development Specialist | [7 empty] | 2028 m24: 0.5; 2029 m36: 1.2
R08708 ¦ Henrique Piqueiro | C6 - Simulation and Digital Twin Specialist | [7 empty] | 2028 m24: 0.5; 2029 m36: 1.2
R06081 ¦ Gonçalo Reis Figueira | D5 - Operations Management and Data Analytics Specialist | [7 empty] | 2028 m24: 0; 2029 m36: 0
A8 | Promotion and dissemination of the results
R02160-1 ¦ Américo Azevedo | D1 - Operations Management Specialist | bar: 2028 m24; 2029 m36
R03160 ¦ Rui Diogo Rebelo | C1 - Digital Architecture Specialist | [7 empty] | 2028 m24: 0; 2029 m36: 0
R07328 ¦ Romão Filipe Santos | C2 - Simulation and Digital Twin Specialist | [7 empty] | 2028 m24: 0.5; 2029 m36: 0
R07929 ¦ Ana Carolina Chaves | C3 - Digital Architeture and Data Infrastructure Specialist | [7 empty] | 2028 m24: 0; 2029 m36: 0
R00283 ¦ César Toscano | C4 - Digital Architeture and Data Infrastructure Specialist | [7 empty] | 2028 m24: 0.5; 2029 m36: 0
R08340 ¦ Hélio Cristiano Castro | D2 - Technology Adoption Specialist | bar: 2028 m24; 2029 m36
R04363 ¦ Cristovão Sousa | D3 - Data Management Specialist | bar: 2028 m24; 2029 m36
R05965 ¦ Luís Guimarães | D4 - Data Analytics Specialist | bar: 2028 m24; 2029 m36
R08941 ¦ Ricardo Ferreira | C5 - Software Development Specialist | [7 empty] | 2028 m24: 0; 2029 m36: 0
R08708 ¦ Henrique Piqueiro | C6 - Simulation and Digital Twin Specialist | [7 empty] | 2028 m24: 0; 2029 m36: 0
R06081 ¦ Gonçalo Reis Figueira | D5 - Operations Management and Data Analytics Specialist | bar: 2028 m24; 2029 m36
A9 | Project management and implementation
R02160-1 ¦ Américo Azevedo | D1 - Operations Management Specialist | [7 empty] | 2027 m12: 0; 2028 m24: 0; 2029 m36: 0
R03160 ¦ Rui Diogo Rebelo | C1 - Digital Architecture Specialist | bar: 2027 m12; 2028 m24; 2029 m36
R07328 ¦ Romão Filipe Santos | C2 - Simulation and Digital Twin Specialist | [7 empty] | 2028 m24: 0; 2029 m36: 0
R07929 ¦ Ana Carolina Chaves | C3 - Digital Architeture and Data Infrastructure Specialist | [7 empty] | 2028 m24: 0; 2029 m36: 0
R00283 ¦ César Toscano | C4 - Digital Architeture and Data Infrastructure Specialist | [7 empty] | 2028 m24: 0; 2029 m36: 0
R08340 ¦ Hélio Cristiano Castro | D2 - Technology Adoption Specialist | [7 empty] | 2028 m24: 0; 2029 m36: 0
R04363 ¦ Cristovão Sousa | D3 - Data Management Specialist | [7 empty] | 2028 m24: 0; 2029 m36: 0
R05965 ¦ Luís Guimarães | D4 - Data Analytics Specialist | [7 empty] | 2028 m24: 0; 2029 m36: 0
R08941 ¦ Ricardo Ferreira | C5 - Software Development Specialist | [7 empty] | 2028 m24: 0; 2029 m36: 0
R08708 ¦ Henrique Piqueiro | C6 - Simulation and Digital Twin Specialist | [7 empty] | 2028 m24: 0; 2029 m36: 0
R06081 ¦ Gonçalo Reis Figueira | D5 - Operations Management and Data Analytics Specialist | [7 empty] | 2028 m24: 0; 2029 m36: 0